## Sheet1
Date | Work-Done | Remarks
2025-01-07 | Literature Survey Studies Completed | Need more access to ieee papers
2025-01-14 | Brainstorming advancement ideas | Doctor side pages could be made where doctors can access multiple patients
2025-01-21 | Finalising all sensors and modules. Beginning of Ui/Ux design
2025-01-25 | Finalized Circuit/Block diagram. Ui/Ux design completed
2025-01-26 | Finalized simulation | Not able to find the required components on proteus. Created Simulation on Wokwi and hardcoded the required sensors
2025-01-28 | Front end for patient side- Home, login, logout page completed | Bugs - Menu and Login options are not beint reset on page navigation
2025-01-30 | Front end for patient side- Menu options: Patient Details, Live vitals page design
2025-01-31 | Front end for patient side- Menu options: Environmental conditions, Alerts, Gps Track
2025-01-02 | Frontend for patient side- Menu options: Patient history page with an option to export | Pdfs are exporting successfully but there is an issue of text overlapping in certain areas
2025-01-03 | Finalized first draft of the report